## 1 GIA
Gender impact assessments
Table 1 - Gender impact assessments progress
Required | Required | Required | Required | Required | Required | Recommended | Recommended
Title | Subject | Description | Status | Confirm if actions taken | Describe actions taken | Confirm intersectionality considered | Explain intersectional lens applied
What is the title of the policy, program or service that was the subject of the GIA? Please use one row for each GIA completed. When reporting on multiple actions taken, include this information in the relevant single cell. | Was the subject of the GIA a policy, program or service? For definitions of policies, programs and services, please refer to the guidance materials at Appendix A: Glossary of terms. Use the drop-down menu in the cell to select your answer. | Provide a description of the policy, program or service subject to the GIA. | Was the policy, program or service new, or up for review? Use the drop-down menu in the cell to select your answer. | Were actions taken to develop or vary the policy, program or service to meet the needs of people of different genders, address gender inequality and promote gender equality as a result of the GIA? Use the drop-down menu in the cell to indicate whether or not actions were taken as a result of the GIA. | Describe the actions taken to develop or vary the policy, program or service to meet the needs of people of different genders, address gender inequality and promote gender equality. When reporting on multiple actions taken, include this information in one cell. You can press alt+enter to include new lines. | Was it considered that gender inequality may be compounded by disadvantage or discrimination that people may experience on the basis of intersectionality? Use the drop-down menu in the cell to select your answer. | Explain how an intersectional lens was applied while completing the GIA. If this was not done, explain why this was not practicable.
Title | Subject | Description | Status | Confirm if actions taken | Describe actions taken | Confirm intersectionality considered | Explain intersectional lens applied
Gender Equality Action Plan | Program | An action plan designed to create and embded a culture of education, equity and awareness within the organisation. | For Review | Yes | Monthly meetings to ensure actions were being taken to implement the goals at hand. | Yes | Diverse group of staff were consulted with actions and possible implications from actions being taken. Recommendations were shared at board level before being implemented.
Sexual Harassment Policy | Policy | The purpose of this policy is to safeguard the organisation and the people working within it from experience such behaviours and providing reporting mechanisms | New | Yes | The policy was recived and created in line with new legislation as well as best practices from several other organisations. | Yes | Diverse group were consulted, inclusing GEAP action group, sports network, executive and board.
Code of Conduct | Policy | The purpose of the code of conduct is to ensure the integrity and strength of character in which each individual at the VIS conducts themselves. | For Review | Yes | The policy was recived and created in line with new legislation as well as best practices from several other organisations. | Yes | Diverse group were consulted, inclusing GEAP action group, sports network, executive and board.
IMPORTANT: When inserting new row(s) to this table, please ensure they are inserted above these two black rows.
Example(s)
Title | Subject | Description | Status | Confirm if actions taken | Describe actions taken | Confirm intersectionality considered | Explain intersectional lens applied
Example: Sports ground use and permits policy | Policy | This policy guides the hire and use of all Council's sportsgrounds and facilities by sports clubs and the public. The policy outlines eligibility criteria for hire and use, selection and booking process, fees, payment options, cancellation options and expectations of use. | For review | Yes | Amended the policy to include a commitment to allocate 30% of the total sportsground hiring capacity to new and recently established sports teams comprising of women and gender diverse people. Amended the policy to include a commitment to support local clubs to conduct respect and responsibility training to promote gender equality. Amended the policy to include a commitment to provide dedicated womens and all-gender secured changerooms and facilities for all womens and gender-diverse teams who hire Council sportsgrounds. | Yes | Council conducted research and participated in consultation to ensure the GIA considered intersectionality. It was identified that language and shared changeroom facilities are percieved as major access barriers for culturally and linguistically diverse (CALD) women. Council has addressed these concerns in amending the policy, committing to implementing private changeroom areas and increased signage in a variety of languages.

## 2.1 Strategies and measures
Strategies and measures
Table 2.1 - Strategies and measures progress
Required | Required | Required | Recommended | Recommended | Recommended | Recommended
Strategies and measures | Status | Status description | Evaluation of success | Timeline | Responsible | Relevant indicator(s)
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | Indicators key
List your organisation’s strategies and measures. Include one strategy or measure per row. These are the planned actions that you have outlined in your GEAP to promote gender equality in your workplace. | Assign each strategy or measure a status from the following list: • ‘Complete’ indicates that all planned activities related to this strategy or measure have been finalised. • ‘In progress’ indicates that the activities under this strategy or measure are progressing but not yet complete. • ‘Ongoing’ indicates that the activities under this strategy or measure do not have an end-date and will be addressed on a continual basis. • ‘Not started’ indicates that the planned activities related to this strategy or measure have not yet commenced, including those that are intended to commence in future years. This should include strategies or measures that have been delayed. • ‘Void’ indicates that this strategy or measure appeared in your defined entity’s GEAP, but has since been cancelled. | Describe your progress in implementing each strategy or measure in your GEAP. In particular, you need to explain: • Why you have selected that status from the drop-down menu; and • Whether the status indicates any delay or change from what was planned in your GEAP and if so, the reason for this change. | Evaluating the success of each of your strategies or measures may include: • tracking against pre-identified success markers. These markers may have been specified in your GEAP. • other evaluation markers that may not have been specified in your GEAP, such as participation levels, outcomes, or changes resulting from the strategy or measure, • other ways the strategy or measure has contributed to promoting gender equality in your defined entity. | If your GEAP included a timeline for action or implementation for your strategies and measures, include this timeline below. If you did not include a timeline in your GEAP, we highly recommend you do so in this progress report by including a timeline below. | Include the role or team responsible for implementing of each strategy or measure. | Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. | [6 empty] | 1. 2. 3. 4. 5. 6. 7. | Gender composition of all levels of the workforce. Gender composition of governing bodies. Equal remuneration for work of equal or comparable value across all levels of the workforce, irrespective of gender. Sexual harassment in the workplace Recruitment and promotion practices in the workplace. Availability and utilisation of terms, conditions and pratices relating to: - family violence leave - flexible working arrangements - working arrangements supporting employees with family or caring responsibilities Gendered segregation within the workplace
Strategies and measures | Status | Status description | Evaluation of success | Timeline | Responsible | 1 | 2 | 3 | 4 | 5 | 6 | 7
Establishing quality and systematic data collection systems and strengthening pre-existing systems to capture intersectionality data (i.e. diversity data) within both the permanent and casual workforce | Complete | HRIS system implemented which allows us to report on measures and progress of the implementation of a completed HR system incorporating diversity measures to complete the data set for future audits and provide better insight into VIS workforce intersectionality | Report on measures and progress of the implementation of a completed HR system incorporating diversity measures to complete the data set for future audits and provide better insight into VIS workforce intersectionality | Twelve Months | Director of People and Community (DPC) |  | x | x |  | x | x | x
Include diversity questions as part of the onboarding/recruitment process for new staff | Complete | Current reporting incorporats diversity measures such as capturing data on cultural identity, gender identity, sexual orientation, disability | Report on incorporated diversity measures such as capturing data on cultural identity, gender identity, sexual orientation, disability | Twelve Months | Director of People and Community (DPC) |  | x |  |  | x | x | x
Disseminate a mini survey to permanent/existing staff to update diversity data | Complete | All staff demongraphic data is up-to-date on the HRIS | Mini census conducted and sent to existing staff that includes specific questions to capture intersectionality data. HR system updated to include this data | Twelve Months | Director of People and Community (DPC) |  | x |  |  | x | x
Consider innovative uptake strategies of the PMS (e.g. work relief/work credit, completion of survey during a team meeting, dissemination of PMS comms to include alignment to organisational intersectional gender equality values and messaging) to maximise participation in these surveys | Complete | Unique tactic of campaign marketing to staff saw 89% of staff complete the survey. | Implement at least 1 innovative uptake strategy for the PMS. 5% increase in response rate across all staff at 2 years, 10% at 4 years | Two Years & Four Years | Director of People and Community (DPC) |  |  |  | x | x | x | x
Integrate questions that capture intersectionality data into already existing staff surveys that complement the PMS every other year | Complete | Captured in PMS each year | Report on additional intersectional questions included in existing staff surveys (when such surveys are conducted in place of the PMS). Include detail of response rates. | Two Years & Four Years | Gender Equality (GE) Working Group |  |  |  | x | x | x | x
Integration of diversity and inclusion in plans, frameworks, strategies, policies, procedures and rules as these documents are drafted or reviewed including; | Complete | Planned and completed with policies being reviewed and consulted at org, executive and board levels. | Report on development or review of two policies each year utilising an intersectional lens. Include detail of process, promotion and implementation | Two per Year | DPC (to be reviewed by GE Working Group prior to final approval) |  |  | x | x | x | x
Development, promotion and implementation of an Inclusion and Diversity policy | In progress | to be completed | Report on development or review of two policies each year utilising an intersectional lens. Include detail of process, promotion and implementation | Two per Year | DPC (to be reviewed by GE Working Group prior to final approval) |  |  | x | x | x | x
Development, promotion and implementation of a Gender Equity policy | Complete | Policy implemented after consultation with employees and board | Report on development or review of two policies each year utilising an intersectional lens. Include detail of process, promotion and implementation | Two per Year | DPC (to be reviewed by GE Working Group prior to final approval) |  |  | x | x | x | xx
Review the VIS motto, vision, mission and values to incorporate diversity and inclusion | Complete | Completed as part of the new renovation project | Report on development or review of two policies each year utilising an intersectional lens. Include detail of process, promotion and implementation | Two per Year | DPC (to be reviewed by GE Working Group prior to final approval)
Promote and celebrate diversity through events (i.e. NAIDOC week), programs (e.g. Rainbow Tick Accreditation) and inclusive initiatives (e.g. Reconciliation Action Plan, cultural awareness training) to support cultural change and enable staff to feel comfortable to disclose personal and sensitive information | Complete | Completed activities to celebrate these awareness days such as messages on noticeboards, Indigneous lunches, basketweaving and cultural awareness training lunches. | Three additional events added to the yearly calendar. Include detail on rationale, process, implementation and engagement. Cultural awareness training delivered. Include details on what, when, who, engagement. | One year (Year Two Cultural awareness training) | HR manager GE Working Group Performance Lifestyle team | [5 empty] | x | x
The appointment of a Gender Equality Action Plan Working Group to lead this work across the organisatio | Complete | Group meeting monthly to track progress and assign actions. | EOI distributed to the workforce to engage representatives/ key influencers from all levels across the workforce. Report on response. Outline the gender balance, terms of reference and FTE assigned to the working group. Monthly working group meetings established. Report on attendance, actions and achievements. | Three Months | GE Working Group HR Manager |  | x | x | x | x | x | x
Periodically provide the Minister with up-to-date skills matrices - including gender and diversity information, and recommendations in relation to VIS board appointments that will meet both the business needs of the organisation and gender and diversity policy requirements of government | Complete | Diversity statistics included and shared in VIS board reports | Provide overview of report to minister and details on when this was completed and submitted | Every two years following GEAP progress report | Chair/CEO | x |  |  |  | x
Reviewing the process (collection, upload, extrapolation) for completing the CGEPS reporting template to ensure gender pay gap data is valid. As part of this conducting a gender pay gap analysis across employment classifications and levels to understand the factors contributing to pay differences | Complete | A completed integrated HR system has been implemented. Include details on review process and analysis | A completed integrated HR system has been implemented. Include details on review process and analysis | Twelve – Eighteen months | DPC Executive Leadership Team (ELT) | x | x |  |  | x | x
Improving response measures to sexual harassment through: |  | None reported | Detail the measures that have been put into place and the process around implementation and promotion. See below. | Two Years ongoing | DPC ELT
Increasing the options available to workers to make a report of workplace sexual harassment (eg. Worksafe anonymous reporting chat line) | Complete | Workplace Officer roles appointed and trained. | Workplace officer roles appointed and trained. Number of staff accessing this support | Two Years ongoing | DPC ELT
Prioritising worker wellbeing and the provision of support to workers (i.e. promotion of 1800RESPECT, Employee Assistance Programs, workplace officer roles) | Complete | Displayed on noticeboards and included in new policies. | Number of staff reporting | Two Years ongoing | DPC ELT
The provision of workplace training in sexual harassment (prevention and response) for key staff, in particular line managers, HR and Executive | Complete | 100% of nominated staff participated in the training | 100% of nominated staff participated in training | Two Years ongoing | DPC ELT
Improving the collection of data at a workplace-level to better understand the scope and nature of sexual harassment in the workplace | Complete | Details of promotion of relevant policies during cultural/diversity celebrations have been achieved through internal comms. | Details of promotion of relevant policies during cultural/diversity celebrations and via internal comms. | Two Years ongoing | DPC ELT
Unconscious bias training for HR department and leadership to address unconscious bias at every stage of the employment cycle (job advertisements, descriptions, composition of interview panels, shortlisting and appointment processes) | Complete | 100% of nominated staff participated in the training | Where, when and how was training rolled out? Attendance and feedback. How are the learnings beings integrated? | Eighteen Months | DPC HR Manager Line management (for PD reporting) |  |  |  | x
More (equitable) opportunities, support and pathways for staff to move into positions of management and higher responsibility | In progress | Recruitment and selection policy currently being reviewed. | Report on measures and progress | Four Years | DPC HR Manager Line management (for PD reporting)
Formalising, promoting and monitoring all forms of flexible working arrangements. Review existing flexible leave policy and strengthen opportunities for flexible options. Promote updated policy and guidelines to applicable staff members. | Complete | Flexible work policy completed | Detail on review and internal awareness raising process | Two Years | DPC GE Working Group ELT |  |  | x |  | x
Prioritise the organisation’s focus on family violence prevention and response through: | Complete | Internal promotion of 16 Days of Activism Against Gendered Violence and Week Without Violence | Internal promotion of 16 Days of Activism Against Gendered Violence and Week Without Violence | Two Years | DPC GE Working Group ELT |  |  |  | x
The provision of workplace-wide bystander training and education to understand the link between gender inequity and family violence | In progress | Bystander training to be implemented | Details of training. Who, When, Where. Engagement and feedback | Two Years | DPC GE Working Group ELT |  |  |  | x
Training for managers, HR and other key staff on how to respond to disclosure and support an employee experiencing family violence | Complete | Training completed | Details of training. Who, When, Where. Engagement and feedback | Two Years | DPC GE Working Group ELT |  |  |  | x
Awareness raising campaigns to increase staff knowledge of family violence leave provisions | Complete | Detailed in the EBA and awareness days | Details on campaign | Two Years | DPC GE Working Group ELT |  |  |  | x | x
Reviewing recruitment and retention strategies in work areas where occupational gender segregation is pronounced, and implement innovative measures to attract women, men and gender-diverse candidates to all roles including: | In progress | Review data on diversity as part of the recruitment process and update recruitment and selection policy. | Include captured gender data of applications and how this is being monitored over time. Report on changes | Two Years | Director High Performance (DHP) |  |  |  |  | x
Improving the visibility of women and gender diverse individuals as coaches and adopt mentorship programs or similar to support female professional development in this area eg. adopt mentorship program for women in Coaching and S&C, and men in Nutrition; Promotion of AIS and Vic Gov Female in Sport scholarship and mentor programs. | In progress | Will continue to work on story telling inititates the VIS is doing to support women in sport. E.g Claire Lamb Gen 32, IWD | Include captured gender data of applications and how this is being monitored over time. Report on changes | Two Years | Director High Performance (DHP) | x | x |  |  | x
Meet with universities and other relevant peak bodies to develop a recruitment pathway for women and gender diverse people into high performance sport | Ongoing | Need to better engage with universities | Share report with universities and relevant peak bodies to promote mentorship programs. Include details of this deliverable | Four Years | Director High Performance (DHP) | x | x |  |  | x
Select one
IMPORTANT: When inserting new row(s) to this table, please ensure they are inserted above these two black rows.
Example(s)
Strategies and measures | Status | Status description | Evaluation of success | Timeline | Responsible | Relevant indicator(s)
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7
Example: Address gaps identified in collecting intersectional data as part of employee and payroll systems | Complete | This strategy was implemented in March 2023. A payroll systems firm was engaged to upgrade our systems to support the collection of intersectional data in relation to sexual orientation, race, Aboriginality, religion, ethnicity, disability and gender identity. We have now begun collecting intersectional data and addressing the gaps identified in our 2021 audit. | Although originally anticipated for implementation in 2022, delays meant this strategy was implemented in March 2023. Intersectional data is being collected as part of new recruitments and promotions, and voluntary updates by existing staff. New intersectional data as part of our 2023 progress audit and future GEAPs will enable us to better understand intersectional gender equality in our organisation and areas for improvement. | 2022 | People and Culture Corporate Support | X | X | X |  | X | X | X

## 2.2 Resourcing your GEAP
Resourcing your GEAP
Table 2.2 - Allocation of resources to implement the strategies and measures in your GEAP
Recommended
You might consider some or all of the following, in addition to any other aspects you consider relevant: • Who implements the strategies and measures in your GEAP? What role do they perform at what level in your defined entity? • How many staff members/FTE are allocated to implementing the strategies and measures? • Was enough resourcing allocated to successfully implement your strategies and measures? If not, how will this be addressed?
Your Comments
- Project Manager (Innovation & Research), Director People & Community and HR Coordinator are responsible for the delivery of the GEAP actions. They are adequately supported by a diverse working group representing different areas of the business including: Director Corporate Services, Performance Coordinator, Performance Lifestyle Manager, Physical Preparation Coach, Physiotherapist.

## 3 Indicators
Workplace Gender Equality Indicators
Table 3 - Workplace gender equality indicators progress
Required | Required | Required | Recommended | [6 empty] | Recommended | Factors key:
|  |  | Factors | [7 empty] | a. b. c. d. e. f. g. | The size of the defined entity, including the defined entity's number of employees. The nature and circumstances of the defined entity, including any barriers to making progress. Requirements that apply to the defined entity under any other Act, including an Act of the Commonwealth. The defined entity's resources. The defined entity's operational priorities and competing operational obligations. The practicability and cost to the defined entity of making progress. Genuine attempts made by the defined entity to make progress.
Indicator | Confirm if progress made | Progress description | a | b | c | d | e | f | g | Factors discussion
This column contains the seven workplace gender equality indicators. Complete the 'required' fields, and you are encouraged to complete the 'recommended' columns, to the right of each indicator. | Indicate whether your organisation has made progress in relation to the workplace gender equality indicators. Use the drop-down menu in the cell to select 'yes' or 'no.' | Demonstrate your progress in relation to each workplace gender equality indicator. In this column, please explain why you believe changes in your data do or do not represent progress against each indicator. Refer explicitly to quantitative changes in the data between your previous workplace gender audit and your progress audit. If you wish, you may also make reference to any strategy or measure from your GEAP that supported, or was designed to support, progress against that indicator. | Indicate below whether or not one of these factors has affected your organisation's progress against each indicator. You are encouraged to reference these factors in your discussion in column L. See the Factors key to the right of this table for a description of each factor. | [6 empty] | If you have selected 'yes' to any of the factors in the recommended columns to the left, you are encouraged to complete this column. This column allows you to discuss each factor that has affected your organisation's progress in relation to any of the workplace gender equality indicators.
Indicator | Confirm if progress made | Progress description | a | b | c | d | e | f | g | Factors discussion
Gender composition of all levels of the workforce | Yes | Over 60% of the workforce is female | Yes | Yes |  |  |  |  | Yes | Clear recruitment practices and storytelling that support women in sport, alongside flexible work policies have allowed us to attract, retain and hire women in the workforce.
Gender composition of governing bodies | Yes | Greater than 50% female representation on the board |  |  | Yes |  |  |  | Yes | Appointed through the Board and assisting with Board observership program.
Equal remuneration for work of equal or comparable value across all levels of the workforce, irrespective of gender | Yes |  |  |  | Yes |  |  |  |  | EBA in place to support this.
Sexual harassment in the workplace | Yes | New policy implemented with increased reporting measures and capabilities (jncluding the training of relevant staff) |  |  |  |  | Yes |  | Yes | Increased training for all staff, workplace officers appointed and genuine discussion through monthly WHS meetings.
Recruitment and promotion practices in the workplace | Yes | Have begun collecting data in order to disseminate areas of improvement |  |  |  | Yes |  |  | Yes | HR team in place to assist this and the collection of data.
Availability and utilisation of terms, conditions and practices relating to: - family violence leave; and - flexible working arrangements; and - working arrangements supporting employees with family or caring responsibilities | Yes | New policies implemented and concerted education to the workforce about the use and purpose of these policies. |  |  |  | Yes | Yes |  | Yes | New policies have been endorsed after consultation with external stakeholders, staff and board.
Gendered segregation within the workplace | No | Most of the part-time roles still are held by women. |  | No | [5 empty] | Several staff have opted for flexible return to work practices after parental leave.
Example(s)
Indicator | Confirm if progress made | Progress description | Factors | [6 empty] | Factors discussion
|  |  | a | b | c | d | e | f | g
Example 1: Recruitment and promotion practices in the workplace | Yes | Recruitment In our 2021 audit, women represented only 35% of new recruits in the year to 30 June 2021. In our 2023 progress audit, this rose 6% to 41%. In 2021, of the women we recruited, 17% were employed on a full-time permanent basis, 14% on a part-time permanent basis and 69% on fixed-term contracts. In 2023, 22% of women recruited were employed on a full-time permanent basis, 20% on a part-time permanent basis and 58% on fixed-term contracts. We were not able to collect non-binary or gender diverse data in 2021. Our employee and payroll systems have since been updated to collect improved gender-diverse data. This has been achieved through the implementation of strategy 5.2 under our 2021 Gender Equality Action Plan (GEAP): ‘Embed inclusive practices into our HR electronic systems. For example, offering a range of gender selection options’. As such, in 2023, our data showed that 2% of new recruits identified as non-binary or gender diverse. Our organisation argues that these figures, in conjunction with successful implementation of relevant GEAP strategies, contribute to progress against Indicator 5. Not only have we been able to notably increase our recruitment of women and gender diverse employees, but we have also been able to offer these new recruits more attractive contract conditions. Stable contracts will also support us to retain employees of all genders and move towards a more gender-balanced workforce in the future. Promotions Our 2021 audit showed that 25% of promotions in the 12 months to 30 June 2021 were awarded to women. These promotions occurred in the lower and middle levels of the organisation only, and not within the executive leadership team. Our 2023 progress audit showed that 30% of all promotions were awarded to women, an increase of 5%. Of these, 10% occurred in the higher levels of the organisation and were ongoing permanent roles. Our organisation historically has a very stable executive leadership team where roles tend to be longer-term contracts or ongoing positions, with few exits. We are pleased to see promotion at the higher level of our organisation into ongoing positions for women. In 2021, we were not able to collect promotion data for non-binary or gender-diverse employees. In 2023, our updated systems allowed us to collect this data. However, there were no promotions awarded to this staff cohort. We believe that a significant aspect of our success in increasing the proportion of promotions awarded to women has been our focus on improving secondment and higher duties opportunities for women and gender-diverse employees. The proportion of secondments awarded to women increased by 5% and the proportion of higher duties by 6% between our 2021 workplace gender audit and our 2023 progress audit. Data on higher duties opportunities for gender diverse and non-binary employees was not collected in 2021, therefore there is no measured change in the data. We consider these improvements, while small, to demonstrate measurable progress against the workplace gender equality indicator ‘recruitment and promotion practices in the workplace’. We also believe the uptick in career development opportunities for women and resulting increase in women’s share of promotions demonstrates that our strategic approach is effective. We hope to see similar improvements for gender diverse employees reflected in our 2025 data. | No | Yes | No | No | No | No | Yes | As a largely male-dominated industry we recognise we have started from a lower baseline for this indicator and there is further to go. Despite this, we have made genuine efforts to attract and recruit a more gender diverse workforce by implementing the strategies identified in our GEAP, in particular: strategy 5.2 ‘Embed inclusive practices into our HR electronic systems. For example, offering a range of gender selection options’. We note that we are two years into the four-year GEAP implementation period, and as such have not fully implemented all GEAP strategies. The majority of our strategies against this indicator remain in early implementation stage. We believe our genuine efforts to implement strategies against this indicator and measurable progress arising from the data, demonstrate progress against indicator 5.
Example 2: Sexual harassment in the workplace | No | Our 2021 Employee Experience Survey data showed that 7% of women and 4% of men who responded to the survey had experienced sexual harassment in the workplace, and of those 5% of women and 6% of men made a formal complaint. In 2023, our Employee Experience Survey data showed that 9% of women and 6% of men who responded to the survey reported having experienced sexual harassment in the workplace, an increase of 2% from 2021 for both cohorts. Of those, 9% of women and 10% of men indicated that they had made a formal complaint. Our 2023 Employee Experience Survey also indicated that women with disability were overrepresented among those who reported experiencing sexual harassment. We have initiated a review process to consider how we might address this between now and the 2025 reporting cycle. No respondents in our 2021 Employee Experience Survey identified as gender diverse. We also didn’t record any formal sexual harassment complaints in our 2021 workforce reporting data from employees of self-described gender. In our 2023 employee experience survey, 2% of respondents identified as non-binary or gender diverse. Of this cohort, 10% indicated experience of sexual harassment, with 50% of this group indicating that they had made a formal complaint. We note that these figures represent an increase in anonymous self-reporting of sexual harassment. This is concerning, as anonymous reporting tends to be more accurate than formal incident reporting processes. In analysing our 2021 and 2023 audit data, we found that our workforce reporting shows minimal change in terms of outcomes for formal complaints of sexual harassment. In 2021, our audit data showed that no outcome was reached for 70% of matters where the complainant was a woman, and 50% of matters where the complainant was a man. In 2023, our progress audit showed that of the incidents of sexual harassment reported by women, no outcome was reached for 65% of matters. This figure was 40% for men. We did not collect data on gender diverse and non-binary employees in 2021, nor their experience of sexual harassment. Our 2023 progress audit showed that of the incidents of sexual harassment reported by gender diverse and non-binary employees, no outcome was reached for 67% of matters. The enduring high levels of formal complaints with no outcome across our 2021 and 2023 audit data suggests that we have work to do in effectively and efficiently resolving sexual harassment complaints. The lack of outcomes for incidents of this type may contribute to our lack of progress in reducing sexual harassment. As a result of this analysis, we are reviewing our GEAP strategies and measures to consider how we might better respond to, and therefore hopefully reduce, sexual harassment in our organisation. We consider that the anonymous nature of the Employee Experience Survey data provides an accurate representation of sexual harassment. The increased sexual harassment reported via the Employee Experience Survey data indicates ‘no progress’ was made by our organisation against this indicator. | No | No | No | Yes | Yes | No | No | (e) Competing priorities and operational obligations Our organisation is a metro health service. During the recent covid-19 pandemic, Victoria’s public health system experienced unprecedented demand. In particular, rates of access to ICU and ventilation increased dramatically. As such, our organisation prioritised its public-facing service delivery. We directed the majority of our stretched resources externally to enable high-quality public health care. Demand outstripped supply, and already-stretched resources were directed to keeping ICU and general wards staffed. As a result, we were not able to deliver comprehensive in-person bespoke staff training in relation to sexual harassment, so instead delivered a low-cost e-learning module. We also lacked the resources to comprehensively review our internal sexual harassment processes. (d) Resources As described cell D9, our resources were significantly stretched due to an increase in demand for ICU services during the covid-19 pandemic. Competing priorities reduced the resources available for internal-facing programs, such as comprehensive sexual harassment training delivery and process review. For this reason, we focussed on low-cost strategies and measures in our GEAP, including delivering a sexual harassment e-learning module, circulating internal communications campaigns and encouraging staff to undertake the Employee Experience Survey. Our communications campaign focussed on drawing attention to existing sexual harassment policies including how the organisation will respond.

## Examples (hidden)
1 Gender impact assessments
| Title | Subject | Description | Status |  |  | Confirm if actions taken |  |  |  | Describe actions taken |  | Confirm intersectionality considered |  | Explain intersectional lens applied
| What is the title of the policy, program or service that was the subject of the GIA? Please use one row for each GIA completed. When reporting on multiple actions taken, include this information in the relevant single cell. | Was the subject of the GIA a policy, program or service? For definitions of policies, programs and services, please refer to the guidance materials at Appendix A: Glossary of terms. Use the drop-down menu in the cell to select your answer. | Provide a description of the policy, program or service subject to the GIA. | Was the policy, program or service new, or up for review? Use the drop-down menu in the cell to select your answer. |  |  | Were actions taken to develop or vary the policy, program or service to meet the needs of people of different genders, address gender inequality and promote gender equality as a result of the GIA? Use the drop-down menu in the cell to indicate whether or not actions were taken as a result of the GIA. |  |  |  | Describe the actions taken to develop or vary the policy, program or service to meet the needs of people of different genders, address gender inequality and promote gender equality. When reporting on multiple actions taken, include this information in one cell. You can press alt+enter to include new lines. |  | Was it considered that gender inequality may be compounded by disadvantage or discrimination that people may experience on the basis of intersectionality? Use the drop-down menu in the cell to select your answer. |  | Explain how an intersectional lens was applied while completing the GIA. If this was not done, explain why this was not practicable.
| Example: Sports ground use and permits policy | Policy | This policy guides the hire and use of all Council's sportsgrounds and facilities by sports clubs and the public. The policy outlines eligibility criteria for hire and use, selection and booking process, fees, payment options, cancellation options and expectations of use. | For review |  |  | Yes |  |  |  | Amended the policy to include a commitment to allocate 30% of the total sportsground hiring capacity to new and recently established sports teams comprising of women and gender diverse people. Amended the policy to include a commitment to support local clubs to conduct respect and responsibility training to promote gender equality. Amended the policy to include a commitment to provide dedicated womens and all-gender secured changerooms and facilities for all womens and gender-diverse teams who hire Council sportsgrounds. |  | Yes |  | Council conducted research and participated in consultation to ensure the GIA considered intersectionality. It was identified that language and shared changeroom facilities are percieved as major access barriers for culturally and linguistically diverse (CALD) women. Council has addressed these concerns in amending the policy, committing to implementing private changeroom areas and increased signage in a variety of languages.
2.1 Strategies and measures
| Strategies and measures | Status | Status description | Evaluation of success | [6 empty] | Timeline | Responsible | Relevant indicator(s)
[13 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7
| List your organisation’s strategies and measures. Include one strategy or measure per row. These are the planned actions that you have outlined in your GEAP to promote gender equality in your workplace. | Assign each strategy or measure a status from the following list: • ‘Complete’ indicates that all planned activities related to this strategy or measure have been finalised. • ‘In progress’ indicates that the activities under this strategy or measure are progressing but not yet complete. • ‘Ongoing’ indicates that the activities under this strategy or measure do not have an end-date and will be addressed on a continual basis. • ‘Not started’ indicates that the planned activities related to this strategy or measure have not yet commenced, including those that are intended to commence in future years. This should include strategies or measures that have been delayed. • ‘Void’ indicates that this strategy or measure appeared in your defined entity’s GEAP, but has since been cancelled. | Describe your progress in implementing each strategy or measure in your GEAP. In particular, you need to explain: • Why you have selected that status from the drop-down menu; and • Whether the status indicates any delay or change from what was planned in your GEAP and if so, the reason for this change. | Evaluating the success of each of your strategies or measures may include: • tracking against pre-identified success markers. These markers may have been specified in your GEAP. • other evaluation markers that may not have been specified in your GEAP, such as participation levels, outcomes, or changes resulting from the strategy or measure, • other ways the strategy or measure has contributed to promoting gender equality in your defined entity. | [6 empty] | If your GEAP included a timeline for action or implementation for your strategies and measures, include this timeline below. If you did not include a timeline in your GEAP, we highly recommend you do so in this progress report by including a timeline below. | Include the role or team responsible for implementing of each strategy or measure. | Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator.
| Example: Address gaps identified in collecting intersectional data as part of employee and payroll systems | Complete | This strategy was implemented in March 2023. A payroll systems firm was engaged to upgrade our systems to support the collection of intersectional data in relation to sexual orientation, race, Aboriginality, religion, ethnicity, disability and gender identity. We have now begun collecting intersectional data and addressing the gaps identified in our 2021 audit. | Although originally anticipated for implementation in 2022, delays meant this strategy was implemented in March 2023. Intersectional data is being collected as part of new recruitments and promotions, and voluntary updates by existing staff. New intersectional data as part of our 2023 progress audit and future GEAPs will enable us to better understand intersectional gender equality in our organisation and areas for improvement. | [6 empty] | 2022 | People and Culture Corporate Support | X | X | X |  | X | X | X
3 Workplace Gender Equality Indicators
| Indicator | Confirm if progress made | Progress description | Factors | [6 empty] | Factors discussion
|  |  |  | a | b | c | d | e | f | g
| This column contains the seven workplace gender equality indicators. Complete the 'required' fields, and you are encouraged to complete the 'recommended' columns, to the right of each indicator. | Indicate whether your organisation has made progress in relation to the workplace gender equality indicators. Use the drop-down menu in the cell to select 'yes' or 'no.' | Demonstrate your progress in relation to each workplace gender equality indicator. In this column, please explain why you believe changes in your data do or do not represent progress against each indicator. Refer explicitly to quantitative changes in the data between your previous workplace gender audit and your progress audit. If you wish, you may also make reference to any strategy or measure from your GEAP that supported, or was designed to support, progress against that indicator. | Indicate below whether or not one of these factors has affected your organisation's progress against each indicator. You are encouraged to reference these factors in your discussion in column L. See the Factors key to the right of this table for a description of each factor. | [6 empty] | If you have selected 'yes' to any of the factors in the recommended columns to the left, you are encouraged to complete this column. This column allows you to discuss each factor that has affected your organisation's progress in relation to any of the workplace gender equality indicators.
| Example 1: Recruitment and promotion practices in the workplace | Yes | Recruitment In our 2021 audit, women represented only 35% of new recruits in the year to 30 June 2021. In our 2023 progress audit, this rose 6% to 41%. In 2021, of the women we recruited, 17% were employed on a full-time permanent basis, 14% on a part-time permanent basis and 69% on fixed-term contracts. In 2023, 22% of women recruited were employed on a full-time permanent basis, 20% on a part-time permanent basis and 58% on fixed-term contracts. We were not able to collect non-binary or gender diverse data in 2021. Our employee and payroll systems have since been updated to collect improved gender-diverse data. This has been achieved through the implementation of strategy 5.2 under our 2021 Gender Equality Action Plan (GEAP): ‘Embed inclusive practices into our HR electronic systems. For example, offering a range of gender selection options’. As such, in 2023, our data showed that 2% of new recruits identified as non-binary or gender diverse. Our organisation argues that these figures, in conjunction with successful implementation of relevant GEAP strategies, contribute to progress against Indicator 5. Not only have we been able to notably increase our recruitment of women and gender diverse employees, but we have also been able to offer these new recruits more attractive contract conditions. Stable contracts will also support us to retain employees of all genders and move towards a more gender-balanced workforce in the future. Promotions Our 2021 audit showed that 25% of promotions in the 12 months to 30 June 2021 were awarded to women. These promotions occurred in the lower and middle levels of the organisation only, and not within the executive leadership team. Our 2023 progress audit showed that 30% of all promotions were awarded to women, an increase of 5%. Of these, 10% occurred in the higher levels of the organisation and were ongoing permanent roles. Our organisation historically has a very stable executive leadership team where roles tend to be longer-term contracts or ongoing positions, with few exits. We are pleased to see promotion at the higher level of our organisation into ongoing positions for women. In 2021, we were not able to collect promotion data for non-binary or gender-diverse employees. In 2023, our updated systems allowed us to collect this data. However, there were no promotions awarded to this staff cohort. We believe that a significant aspect of our success in increasing the proportion of promotions awarded to women has been our focus on improving secondment and higher duties opportunities for women and gender-diverse employees. The proportion of secondments awarded to women increased by 5% and the proportion of higher duties by 6% between our 2021 workplace gender audit and our 2023 progress audit. Data on higher duties opportunities for gender diverse and non-binary employees was not collected in 2021, therefore there is no measured change in the data. We consider these improvements, while small, to demonstrate measurable progress against the workplace gender equality indicator ‘recruitment and promotion practices in the workplace’. We also believe the uptick in career development opportunities for women and resulting increase in women’s share of promotions demonstrates that our strategic approach is effective. We hope to see similar improvements for gender diverse employees reflected in our 2025 data. | No | Yes | No | No | No | No | Yes | As a largely male-dominated industry we recognise we have started from a lower baseline for this indicator and there is further to go. Despite this, we have made genuine efforts to attract and recruit a more gender diverse workforce by implementing the strategies identified in our GEAP, in particular: strategy 5.2 ‘Embed inclusive practices into our HR electronic systems. For example, offering a range of gender selection options’. We note that we are two years into the four-year GEAP implementation period, and as such have not fully implemented all GEAP strategies. The majority of our strategies against this indicator remain in early implementation stage. We believe our genuine efforts to implement strategies against this indicator and measurable progress arising from the data, demonstrate progress against indicator 5.
| Example 2: Sexual harassment in the workplace | No | Our 2021 Employee Experience Survey data showed that 7% of women and 4% of men who responded to the survey had experienced sexual harassment in the workplace, and of those 5% of women and 6% of men made a formal complaint. In 2023, our Employee Experience Survey data showed that 9% of women and 6% of men who responded to the survey reported having experienced sexual harassment in the workplace, an increase of 2% from 2021 for both cohorts. Of those, 9% of women and 10% of men indicated that they had made a formal complaint. Our 2023 Employee Experience Survey also indicated that women with disability were overrepresented among those who reported experiencing sexual harassment. We have initiated a review process to consider how we might address this between now and the 2025 reporting cycle. No respondents in our 2021 Employee Experience Survey identified as gender diverse. We also didn’t record any formal sexual harassment complaints in our 2021 workforce reporting data from employees of self-described gender. In our 2023 employee experience survey, 2% of respondents identified as non-binary or gender diverse. Of this cohort, 10% indicated experience of sexual harassment, with 50% of this group indicating that they had made a formal complaint. We note that these figures represent an increase in anonymous self-reporting of sexual harassment. This is concerning, as anonymous reporting tends to be more accurate than formal incident reporting processes. In analysing our 2021 and 2023 audit data, we found that our workforce reporting shows minimal change in terms of outcomes for formal complaints of sexual harassment. In 2021, our audit data showed that no outcome was reached for 70% of matters where the complainant was a woman, and 50% of matters where the complainant was a man. In 2023, our progress audit showed that of the incidents of sexual harassment reported by women, no outcome was reached for 65% of matters. This figure was 40% for men. We did not collect data on gender diverse and non-binary employees in 2021, nor their experience of sexual harassment. Our 2023 progress audit showed that of the incidents of sexual harassment reported by gender diverse and non-binary employees, no outcome was reached for 67% of matters. The enduring high levels of formal complaints with no outcome across our 2021 and 2023 audit data suggests that we have work to do in effectively and efficiently resolving sexual harassment complaints. The lack of outcomes for incidents of this type may contribute to our lack of progress in reducing sexual harassment. As a result of this analysis, we are reviewing our GEAP strategies and measures to consider how we might better respond to, and therefore hopefully reduce, sexual harassment in our organisation. We consider that the anonymous nature of the Employee Experience Survey data provides an accurate representation of sexual harassment. The increased sexual harassment reported via the Employee Experience Survey data indicates ‘no progress’ was made by our organisation against this indicator. | No | No | No | Yes | Yes | No | No | (e) Competing priorities and operational obligations Our organisation is a metro health service. During the recent covid-19 pandemic, Victoria’s public health system experienced unprecedented demand. In particular, rates of access to ICU and ventilation increased dramatically. As such, our organisation prioritised its public-facing service delivery. We directed the majority of our stretched resources externally to enable high-quality public health care. Demand outstripped supply, and already-stretched resources were directed to keeping ICU and general wards staffed. As a result, we were not able to deliver comprehensive in-person bespoke staff training in relation to sexual harassment, so instead delivered a low-cost e-learning module. We also lacked the resources to comprehensively review our internal sexual harassment processes. (d) Resources As described cell D9, our resources were significantly stretched due to an increase in demand for ICU services during the covid-19 pandemic. Competing priorities reduced the resources available for internal-facing programs, such as comprehensive sexual harassment training delivery and process review. For this reason, we focussed on low-cost strategies and measures in our GEAP, including delivering a sexual harassment e-learning module, circulating internal communications campaigns and encouraging staff to undertake the Employee Experience Survey. Our communications campaign focussed on drawing attention to existing sexual harassment policies including how the organisation will respond.

## (Hidden) REF (hidden)
Policy | New | Yes | Select one | Yes
Program | For Review | No | Complete | No action taken
Service |  |  | In progress
Ongoing
Not started
Void/cancelled